Plan of Work – CSA-ES Database
Dr. Matthew Kekoa Lau, PhD.
# Context
The City and County of Honolulu’s Office of Climate Resilience has contracted OACA to produce a Climate Smart Agriculture database intended to inform food system professionals and policy makers on the potential ecosystem service impacts of CSA activities. The consultant (MK Lau) has been sub-contracted by OACA to complete the deliverables listed below in partial fulfillment of the larger contracted deliverable to HC&C.
# Key Personnel
Dr. Matthew Kekoa Lau, PhD. – will combine his expertise in ecological systems theory and big data analysis with the practice of sustainable agriculture to produce the contracted deliverables.
# Deliverables
- CSA-ES literature synthesis
- CSA-ES Resource Database
# Activities
- Literature search
- Literature analysis
- Literature synthesis
- Populate CSA-ES resource database
- Design public facing tool
- Implement public facing tool
# Milestones
- Feb 28, 2024
  - Submit Plan of Work to OACA
- Mar 4, 2024
  - Initiate Reviews
  - Finalize database structure
- Mar 15, 2024
  - Compile Academic Review
  - Initiate Web Resource Search
- Mar 22, 2024
  - Synthesize Academic Review
  - Compile Web Resource Search
  - Initiate Policy Search
- Apr 1, 2024
  - Synthesize Web Resource Search
  - Synthesize Policy Search
  - Plan Web Product
- Apr 8, 2024
  - Present synthesized review results
- Apr 15, 2024
  - Present Web Product for review
- Apr 22, 2024
  - Present integrated feedback for review and submission
- Apr 29, 2024
  - Submit
# Communication and Feedback
Personnel will be in weekly communications by email.
# Evaluation
Evaluations of activities and deliverables will be recorded in meeting notes and emails.